## Summary
Fuel App Development and Deployment
2025-07-28
| Project Phases |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25
Ideation and Business Alignment | bar: 2025-07-28 W1 to 2025-07-28 W2
Design and Architecture | bar: 2025-07-28 W3 to 2025-07-28 W10
Build & Configure (BTP Dev) | bar: 2025-07-28 W9 to 2025-07-28 W16
Test & Validate | bar: 2025-07-28 W17 to 2025-07-28 W24
Deployment & Go Live | bar: 2025-07-28 W25
Support and Continuous Innovation
| Resources Estimate (In Hours) |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | Total
| Project Manager | [27 empty] | 40
| Solution Architect - SAP |  | 4 | 4 | 8 | 8 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8
Solution Architect
BTP Developer
Integration Specialist
| UI/UX Developer |  | 2025-07-28 W1: 0; 2025-07-28 W2: 0
| QA Engineer |  | 2025-07-28 W1: 0; 2025-07-28 W2: 0; 2025-07-28 W3: 0; 2025-07-28 W4: 0; 2025-07-28 W5: 0; 2025-07-28 W6: 0; 2025-07-28 W7: 0; 2025-07-28 W8: 0
Knowledge Management
Security - Compliance
Business Analyst
DevOps Engineer
Total
Assumptions:
1)
2) |  | FTE | 2025-07-28 W1: Involvement
3) | BTP | 1 | bar: 2025-07-28 W1
4) | Functional | 1 | bar: 2025-07-28 W1
5) | ABAPER | 1 | bar: 2025-07-28 W1
6) | Integration | 1 | 2025-07-28 W1: 0.25
7) | PMO | 1 | 2025-07-28 W1: 0.25
8) | other | 1 | 2025-07-28 W1: 0.5
9)
45870

## Sheet1
Fuel App Development and Deployment
2025-07-28
| Project Phases | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25
Ideation and Business Alignment | bar: 2025-07-28 W1 to 2025-07-28 W2
Design and Architecture | bar: 2025-07-28 W3 to 2025-07-28 W10
Build & Configure (BTP Dev) | bar: 2025-07-28 W9 to 2025-07-28 W16
Test & Validate | bar: 2025-07-28 W17 to 2025-07-28 W24
Deployment & Go Live | bar: 2025-07-28 W25
Support and Continuous Innovation
| Resources Estimate (In Hours) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | Total
| Project Manager | [26 empty] | 40
| Solution Architect - SAP | 4 | 4 | 8 | 8 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8
Solution Architect
BTP Developer
Integration Specialist
| UI/UX Developer | 2025-07-28 W1: 0; 2025-07-28 W2: 0
| QA Engineer | 2025-07-28 W1: 0; 2025-07-28 W2: 0; 2025-07-28 W3: 0; 2025-07-28 W4: 0; 2025-07-28 W5: 0; 2025-07-28 W6: 0; 2025-07-28 W7: 0; 2025-07-28 W8: 0
Business Analyst
DevOps Engineer
Total
Assumptions:
1)
2)
3)
4)
5)
6)
7)
8)
9)
45870

## Detailed Activities
[7 empty] | 2025 | [22 empty] | 2026
|  |  | Week starting |  |  | Status | 2025-07-28
Phase | Week | Activity ID | Ph | Activity | Responsible |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31
Ideation and Business Alignment | bar: 2025-07-28 W1 to 2025-07-28 W2
1 | 1 | 1.1.1 |  | Stakeholder interviews with airline operations team | PM, BA, Solution Architect | Complete | bar: 2025-07-28 W1
1 | 1 | 1.1.2 |  | Document current manual accrual processes | BA, Subject Matter Expert | Complete | bar: 2025-07-28 W1
1 | 1 | 1.1.3 |  | Analyze fuel visibility gaps and reporting challenges | BA, Operations Team | Complete | bar: 2025-07-28 W1
1 | 1 | 1.2.1 |  | Assess SAP Industry Cloud for Airlines capabilities | Solution Architect, SAP Consultant | Complete | bar: 2025-07-28 W1
1 | 1 | 1.2.2 |  | Review industry-specific accelerators and templates | Solution Architect | Pending | bar: 2025-07-28 W1
1 | 2 | 2.1.1 |  | Evaluate BTP service offerings (CAP, UI5, Work Zone) | Solution Architect, BTP Developer | Complete | bar: 2025-07-28 W2
1 | 2 | 2.1.2 |  | Assess API availability and integration capabilities | Integration Specialist | Ongoing | bar: 2025-07-28 W2
1 | 2 | 2.1.3 |  | Validate connectivity with S/4HANA and other systems | Integration Specialist | Ongoing | bar: 2025-07-28 W2
1 | 2 | 2.2.1 |  | Complete SAP PartnerEdge registration | PM, Solution Architect | Complete | bar: 2025-07-28 W2
1 | 2 | 2.2.2 |  | Set up development and sandbox environments | DevOps Engineer, BTP Developer | Complete | bar: 2025-07-28 W2
Design and Architecture | bar: 2025-07-28 W3 to 2025-07-28 W8
2 | 3 | 2.1.1 |  | Design L1-L4 business process flows | BA, Solution Architect | Complete | bar: 2025-07-28 W3
2 | 3 | 2.1.2 |  | Define process triggers and decision points | BA, Business Users | Complete | bar: 2025-07-28 W3
2 | 4 | 2.2.1 |  | Define data models for fuel and accruals | Solution Architect, Data Architect | Complete | bar: 2025-07-28 W4
2 | 4 | 2.2.2 |  | Design data security and access control framework | Security Architect, Solution Architect | Complete | bar: 2025-07-28 W4
2 | 5 | 2.3.1 |  | Create wireframes for BTP applications | UX Designer, BA | Complete | bar: 2025-07-28 W5
2 | 5 | 2.3.2 |  | Design user experience for fuel visibility dashboards | UX Designer, Business Users | Complete | bar: 2025-07-28 W5
2 | 6 | 2.4.1 |  | Design SAP Integration Suite connectivity patterns | Integration Specialist, Solution Architect | Complete | bar: 2025-07-28 W6
2 | 6 | 2.4.2 |  | Plan API management and security protocols | Integration Specialist, Security Architect | In progress | bar: 2025-07-28 W6
2 | 7 | 2.5.1 |  | Create high-level design (HLD) document | Solution Architect, Technical Lead | In progress | bar: 2025-07-28 W7
2 | 7 | 2.5.2 |  | Design microservices architecture on BTP | Solution Architect, BTP Developer | In progress | bar: 2025-07-28 W7
2 | 8 | 2.6.1 |  | Finalize API specifications and event contracts | Integration Specialist, BTP Developer | In progress | bar: 2025-07-28 W8
2 | 8 | 2.6.2 |  | Complete architecture diagrams | Solution Architect | bar: 2025-07-28 W8
Build & Configure (BTP Dev) | bar: 2025-07-28 W9 to 2025-07-28 W16
3 | 9 | 3.1.1 |  | Set up BTP subaccounts and entitlements | DevOps Engineer, BTP Admin | Complete | bar: 2025-07-28 W9
3 | 9 | 3.1.2 |  | Configure Cloud Foundry and Kyma runtime | DevOps Engineer | Complete | bar: 2025-07-28 W9
3 | 9 | 3.1.3 |  | Set up HANA Cloud database instances | Database Admin, DevOps Engineer | Complete | bar: 2025-07-28 W9
3 | 10 | 3.2.1 |  | Develop core CAP services for fuel management | BTP Developer (2) | Complete | bar: 2025-07-28 W10
3 | 10 | 3.2.2 |  | Implement data models and OData services | BTP Developer | Complete | bar: 2025-07-28 W10
3 | 11 | 3.3.1 |  | Configure Cloud Integration (CPI) flows | Integration Specialist | Complete | bar: 2025-07-28 W11
3 | 11 | 3.3.2 |  | Develop API proxies in API Management | Integration Specialist | Ongoing | bar: 2025-07-28 W11
3 | 12 | 3.4.1 |  | Develop connectors for airline operational systems | Integration Specialist, BTP Developer | Ongoing | bar: 2025-07-28 W12
3 | 12 | 3.4.2 |  | Implement fuel supplier data integration | Integration Specialist | bar: 2025-07-28 W12
3 | 13 | 3.5.1 |  | Develop fuel visibility dashboard (UI5) | UI Developer, BTP Developer | bar: 2025-07-28 W13
3 | 13 | 3.5.2 |  | Create accrual management interfaces | UI Developer | bar: 2025-07-28 W13
3 | 14 | 3.6.1 |  | Configure SAP Work Zone for role-based access | BTP Developer, Security Admin | bar: 2025-07-28 W14
3 | 14 | 3.6.2 |  | Integrate applications into Work Zone | BTP Developer | bar: 2025-07-28 W14
3 | 15 | 3.7.1 |  | Configure CPE for fuel price management | BTP Developer, Business Analyst | bar: 2025-07-28 W15
3 | 15 | 3.7.2 |  | Set up pricing models and calculation rules | Business Analyst, BTP Developer | bar: 2025-07-28 W15
3 | 16 | 3.8.1 |  | Develop custom fuel logging capabilities | BTP Developer (2) | bar: 2025-07-28 W16
3 | 16 | 3.8.2 |  | Create cockpit dashboard for operations | UI Developer, BTP Developer | bar: 2025-07-28 W16
Test & Validate | bar: 2025-07-28 W17 to 2025-07-28 W24
4 | 17 | 4.1.1 |  | Execute unit tests for all CAP services | QA Engineer, BTP Developer | bar: 2025-07-28 W17
4 | 17 | 4.1.2 |  | Perform code quality and security scans | QA Engineer, Security Architect | bar: 2025-07-28 W17
4 | 18 | 4.2.1 |  | Test end-to-end integration flows | QA Engineer, Integration Specialist | bar: 2025-07-28 W18
4 | 18 | 4.2.2 |  | Validate data synchronization between systems | QA Engineer, Data Analyst | bar: 2025-07-28 W18
4 | 19 | 4.3.1 |  | Execute business process testing scenarios | QA Engineer, Business Users | bar: 2025-07-28 W19
4 | 19 | 4.3.2 |  | Conduct user acceptance testing with airline staff | Business Users, QA Engineer | bar: 2025-07-28 W19
4 | 20 | 4.4.1 |  | Execute performance testing for high-volume scenarios | QA Engineer, Performance Tester | bar: 2025-07-28 W20
4 | 20 | 4.4.2 |  | Test concurrent user access and system scalability | Performance Tester | bar: 2025-07-28 W20
4 | 21 | 4.5.1 |  | Simulate bulk flight operations and fuel consumption | QA Engineer, Business Users | bar: 2025-07-28 W21
4 | 21 | 4.5.2 |  | Test into-plane fuel tracking and validation | QA Engineer, Operations Team | bar: 2025-07-28 W21
4 | 22 | 4.6.1 |  | Execute full end-to-end business scenarios | QA Engineer, All stakeholders | bar: 2025-07-28 W22
4 | 22 | 4.6.2 |  | Test disaster recovery and backup procedures | DevOps Engineer, QA Engineer | bar: 2025-07-28 W22
4 | 23 | 4.7.1 |  | Incorporate feedback from airline business users | BTP Developer, Business Users | bar: 2025-07-28 W23
4 | 23 | 4.7.2 |  | Address SAP IBU recommendations | Solution Architect, BTP Developer | bar: 2025-07-28 W23
4 | 24 | 4.8.1 |  | Execute security penetration testing | Security Tester, QA Engineer | bar: 2025-07-28 W24
4 | 24 | 4.8.2 |  | Validate compliance with aviation regulations | Compliance Officer, QA Engineer | bar: 2025-07-28 W24
4 | 24 | 4.9.1 |  | Validate all CAP backend services and OData endpoints | QA Engineer, BTP Developer | In Progress
4 | 24 | 4.9.2 |  | Verify database schema and data integrity | QA Engineer, Database Admin | Pending
4 | 25 | 4.9.3 |  | Validate authorization and role-based access control | Security Architect, QA Engineer | Pending
4 | 25 | 4.10.1 |  | Execute UI5 component and unit tests | UI Developer, QA Engineer | Pending
4 | 25 | 4.10.2 |  | Perform cross-browser and responsive design testing | QA Engineer, UI Developer | Pending
4 | 26 | 4.10.3 |  | Validate Fiori Elements annotations and previews | UI Developer, BTP Developer | Pending
4 | 26 | 4.11.1 |  | Execute end-to-end backend-frontend integration tests | QA Engineer, Full Stack Team | Pending
4 | 26 | 4.11.2 |  | Test HTML5 Application Repository deployment | QA Engineer, DevOps Engineer | Pending
4 | 27 | 4.11.3 |  | Validate MTA deployment and service bindings | DevOps Engineer, QA Engineer | Pending
Deployment & Go Live | bar: 2025-07-28 W25
5 | 25 | 5.1.1 |  | Configure production BTP environment | DevOps Engineer, BTP Admin | bar: 2025-07-28 W25
5 | 25 | 5.1.2 |  | Deploy applications and integration flows | DevOps Engineer, BTP Developer | bar: 2025-07-28 W25
5 | 25 | 5.2.1 |  | Execute cutover plan and data migration | DevOps Engineer, Data Migration Team | bar: 2025-07-28 W25
5 | 25 | 5.2.2 |  | Activate production integrations and workflows | Integration Specialist, Operations Team | bar: 2025-07-28 W25
5 | 25 | 5.3.1 |  | Complete handover to operations team | PM, Operations Manager | bar: 2025-07-28 W25
Support and Continuous Innovation | bar: 2025-07-28 W25
6 | Ongoing | 6.1.1 |  | Monitor application performance and availability | Operations Team, Support Engineer
6 | Ongoing | 6.1.2 |  | Respond to user issues and service requests | Support Engineer, Help Desk
6 | Ongoing | 6.2.1 |  | Collect user feedback and enhancement requests | Product Owner, Business Analyst
6 | Ongoing | 6.2.2 |  | Plan additional features and improvements | Product Owner, Solution Architect
6 | Ongoing | 6.3.1 |  | Review and update technology stack | Solution Architect, DevOps Engineer
6 | Ongoing | 6.3.2 |  | Evaluate new SAP BTP capabilities | Solution Architect, BTP Developer

## Sheet2
15%
30%
30%
15%
10%
750000