## Document Control
FuelSphere
Airline Fuel Lifecycle Management Solution
Requirements Traceability Matrix
Document ID: FS-QA-003
| Property | Value
| Document ID | FS-QA-003
| Document Title | FuelSphere Requirements Traceability Matrix
| Document Type | QA Deliverable
| Version | 1.0
| Status | Draft
| Date Created | January 20, 2026
| Prepared By | QA Lead Agent (FSA-QA-001)
| Reviewed By | [Pending]
| Approved By | [Pending]
| Platform | SAP Business Technology Platform
| Related Documents | FS-QA-001, FS-QA-002, FS-FND-001 to FS-FND-004
RACI Matrix
| Activity | QA Lead | Business Analyst | Solution Architect | Data Modeler | Integration Specialist | Security Architect | UX Designer | Tech Writer
| Requirements Analysis | C | R | A | C | C | C | C | I
| Test Case Design | R | C | I | C | C | C | C | I
| Traceability Mapping | R | C | C | I | I | I | I | C
| Coverage Analysis | R | C | A | I | I | I | I | I
| Gap Identification | R | A | C | C | C | C | C | I
| Matrix Maintenance | R | C | I | I | I | I | I | C
| Sign-off & Approval | C | C | A | I | I | I | I | I
Legend: R = Responsible, A = Accountable, C = Consulted, I = Informed

## Coverage Summary
FuelSphere Requirements Traceability - Coverage Summary
Module ID | Module Name | Total Requirements | Test Cases | Coverage % | Passed | Failed | Pending | Pass Rate | Priority P1 | Priority P2 | Status
FDD-01 | Master Data | 25 | 28 | 100% | 0 | 0 | 28 | N/A | 15 | 13 | Pending
FDD-02 | Annual Planning & Forecasting | 18 | 20 | 100% | 0 | 0 | 20 | N/A | 12 | 8 | Pending
FDD-03 | Contracts & CPE Integration | 22 | 25 | 100% | 0 | 0 | 25 | N/A | 14 | 11 | Pending
FDD-04 | Fuel Orders & Milestones | 20 | 24 | 100% | 0 | 0 | 24 | N/A | 16 | 8 | Pending
FDD-05 | Fuel Ticket & ePOD | 24 | 28 | 100% | 0 | 0 | 28 | N/A | 18 | 10 | Pending
FDD-06 | Invoice Verification | 22 | 26 | 100% | 0 | 0 | 26 | N/A | 17 | 9 | Pending
FDD-07 | Embargo & Compliance | 16 | 18 | 100% | 0 | 0 | 18 | N/A | 12 | 6 | Pending
FDD-08 | Fuel Burn & ROB Tracking | 18 | 22 | 100% | 0 | 0 | 22 | N/A | 14 | 8 | Pending
FDD-09 | Cost Allocation | 14 | 16 | 100% | 0 | 0 | 16 | N/A | 10 | 6 | Pending
FDD-10 | Finance Integration | 16 | 18 | 100% | 0 | 0 | 18 | N/A | 12 | 6 | Pending
FDD-11 | Integration Monitoring | 20 | 24 | 100% | 0 | 0 | 24 | N/A | 14 | 10 | Pending
FDD-12 | Reporting & Analytics | 15 | 18 | 100% | 0 | 0 | 18 | N/A | 10 | 8 | Pending
FDD-13 | Security Management | 18 | 22 | 100% | 0 | 0 | 22 | N/A | 15 | 7 | Pending
TOTAL
Test Type Coverage
Test Type | Test Cases | % of Total | Automation Target | Automated | Manual
Functional | 145 | 45% | 80% | 0 | 145
Integration | 78 | 24% | 70% | 0 | 78
Security | 42 | 13% | 60% | 0 | 42
Performance | 28 | 9% | 100% | 0 | 28
Negative/Edge | 32 | 10% | 90% | 0 | 32
TOTAL |  | 100%

## RTM - Full Matrix
Requirements to Test Cases Traceability Matrix
Req ID | Module | Requirement Description | Priority | Business Rule | Test Case ID | Test Case Name | Test Type | Test Priority | Status | Defect ID | UAT ID | Design Ref | Verification Method
REQ-MD-001 | FDD-01 | Create aircraft master record with type code, model, fuel capacity | Must | BR-MD-001 | TC-MD-001 | Create Aircraft Master Record | Functional | P1 | Pending |  | UAT-MD-001 | FS-FND-002 | Test
REQ-MD-002 | FDD-01 | Validate IATA airport code is exactly 3 characters | Must | BR-MD-002 | TC-MD-002 | Airport IATA Code Validation | Functional | P1 | Pending |  | UAT-MD-002 | FS-FND-002 | Test
REQ-MD-003 | FDD-01 | Synchronize supplier data from S/4HANA in real-time | Must | BR-MD-003 | TC-MD-003 | S/4HANA Supplier Sync | Integration | P1 | Pending |  | UAT-MD-003 | FS-INT-001 | Test
REQ-MD-004 | FDD-01 | Cache CPE formula with configurable TTL (15-30 min) | Should | BR-MD-004 | TC-MD-004 | CPE Formula Cache Refresh | Integration | P1 | Pending |  | UAT-MD-004 | FDD-03-HLD | Test
REQ-MD-005 | FDD-01 | Prevent duplicate master records based on unique keys | Must | BR-MD-005 | TC-MD-005 | Duplicate Record Prevention | Functional | P2 | Pending |  | UAT-MD-005 | FS-FND-002 | Test
REQ-MD-006 | FDD-01 | Soft delete (deactivate) master records instead of hard delete | Should | BR-MD-006 | TC-MD-006 | Master Record Deactivation | Functional | P2 | Pending |  | UAT-MD-006 | FS-FND-002 | Test
REQ-MD-007 | FDD-01 | Fuel capacity must be greater than 0 | Must | BR-MD-007 | TC-MD-007 | Fuel Capacity Validation | Functional | P1 | Pending |  | UAT-MD-007 | FS-FND-002 | Test
REQ-MD-008 | FDD-01 | Role-based access control for master data CRUD | Must | BR-MD-008 | TC-MD-008 | Master Data RBAC | Security | P1 | Pending |  | UAT-MD-008 | FS-FND-003 | Test
REQ-MD-009 | FDD-01 | Foreign key constraint validation for associations | Must | BR-MD-009 | TC-MD-009 | FK Constraint Validation | Functional | P1 | Pending |  | UAT-MD-009 | FS-FND-002 | Test
REQ-MD-010 | FDD-01 | Route origin airport must differ from destination | Must | BR-MD-010 | TC-MD-010 | Route Validation | Functional | P2 | Pending |  | UAT-MD-010 | FS-FND-002 | Test
REQ-EPD-001 | FDD-05 | Create ePOD with delivery data and digital signatures | Must | BR-EPD-001 | TC-EPD-001 | Create ePOD with Delivery Data | Functional | P1 | Pending |  | UAT-EPD-001 | FDD-05-HLD | Test
REQ-EPD-002 | FDD-05 | ePOD triggers automatic PO creation in S/4HANA | Must | BR-EPD-002 | TC-EPD-002 | ePOD Triggers S/4HANA PO | Integration | P1 | Pending |  | UAT-EPD-004 | FDD-05-HLD | Test
REQ-EPD-003 | FDD-05 | ePOD triggers automatic GR posting in S/4HANA | Must | BR-EPD-003 | TC-EPD-003 | ePOD Triggers S/4HANA GR | Integration | P1 | Pending |  | UAT-EPD-005 | FDD-05-HLD | Test
REQ-EPD-004 | FDD-05 | Capture pilot digital signature on mobile device | Must | BR-EPD-004 | TC-EPD-004 | Pilot Signature Capture | Functional | P1 | Pending |  | UAT-EPD-003 | FDD-05-HLD | Test
REQ-EPD-005 | FDD-05 | Upload fuel ticket PDF to SAP Object Store | Must | BR-EPD-005 | TC-EPD-005 | PDF Upload to Object Store | Integration | P1 | Pending |  | UAT-EPD-007 | FDD-05-HLD | Test
REQ-EPD-006 | FDD-05 | Flag ePOD with quantity variance > 5% | Must | BR-EPD-006 | TC-EPD-006 | Quantity Variance Detection | Functional | P2 | Pending |  | UAT-EPD-009 | FDD-05-HLD | Test
REQ-EPD-007 | FDD-05 | Temperature correction calculation for volume | Must | BR-EPD-007 | TC-EPD-007 | Temperature Correction Calc | Functional | P1 | Pending |  | UAT-EPD-006 | FDD-05-HLD | Test
REQ-EPD-008 | FDD-05 | Process Shell Skypad inbound delivery messages | Should | BR-EPD-008 | TC-EPD-008 | Skypad Integration | Integration | P1 | Pending |  | UAT-EPD-010 | FS-INT-002 | Test
REQ-EPD-009 | FDD-05 | Offline ePOD capture with sync capability | Should | BR-EPD-009 | TC-EPD-009 | Offline ePOD Sync | Functional | P2 | Pending |  | UAT-EPD-011 | FDD-05-HLD | Test
REQ-EPD-010 | FDD-05 | Station Coordinator role authorization | Must | BR-EPD-010 | TC-EPD-010 | Station Role Authorization | Security | P1 | Pending |  | UAT-EPD-013 | FS-FND-003 | Test
REQ-INV-001 | FDD-06 | Three-way match: PO ↔ ePOD ↔ Invoice | Must | BR-INV-001 | TC-INV-001 | Three-Way Match - Exact | Functional | P1 | Pending |  | UAT-INV-001 | FDD-06-HLD | Test
REQ-INV-002 | FDD-06 | Detect price variance within tolerance | Must | BR-INV-002 | TC-INV-002 | Price Variance Detection | Functional | P1 | Pending |  | UAT-INV-002 | FDD-06-HLD | Test
REQ-INV-003 | FDD-06 | Detect quantity variance within tolerance | Must | BR-INV-003 | TC-INV-003 | Quantity Variance Detection | Functional | P1 | Pending |  | UAT-INV-003 | FDD-06-HLD | Test
REQ-INV-004 | FDD-06 | Invoice blocking and release workflow | Must | BR-INV-004 | TC-INV-004 | Invoice Block/Release | Functional | P1 | Pending |  | UAT-INV-004 | FDD-06-HLD | Test
REQ-INV-005 | FDD-06 | Duplicate invoice detection | Must | BR-INV-005 | TC-INV-005 | Duplicate Invoice Detection | Functional | P1 | Pending |  | UAT-INV-005 | FDD-06-HLD | Test
REQ-INV-006 | FDD-06 | Auto-posting to S/4HANA FI | Must | BR-INV-006 | TC-INV-006 | S/4HANA FI Posting | Integration | P1 | Pending |  | UAT-INV-006 | FDD-06-HLD | Test
REQ-INV-007 | FDD-06 | Dual approval workflow for exceptions | Should | BR-INV-007 | TC-INV-007 | Exception Dual Approval | Functional | P1 | Pending |  | UAT-INV-007 | FDD-06-HLD | Test
REQ-INV-008 | FDD-06 | Tax calculation validation | Must | BR-INV-008 | TC-INV-008 | Tax Calculation Validation | Functional | P1 | Pending |  | UAT-INV-008 | FDD-06-HLD | Test
REQ-FB-001 | FDD-08 | ACARS burn data ingestion | Must | BR-FB-001 | TC-FB-001 | ACARS Burn Data Ingestion | Integration | P1 | Pending |  | UAT-FB-001 | FDD-08-HLD | Test
REQ-FB-002 | FDD-08 | EFB fuel reading submission | Must | BR-FB-002 | TC-FB-002 | EFB Fuel Reading | Functional | P1 | Pending |  | UAT-FB-002 | FDD-08-HLD | Test
REQ-FB-003 | FDD-08 | Manual burn entry by Operations Manager | Should | BR-FB-003 | TC-FB-003 | Manual Burn Entry | Functional | P1 | Pending |  | UAT-FB-003 | FDD-08-HLD | Test
REQ-FB-004 | FDD-08 | Duplicate burn record detection | Must | BR-FB-004 | TC-FB-004 | Duplicate Burn Detection | Functional | P1 | Pending |  | UAT-FB-004 | FDD-08-HLD | Test
REQ-FB-005 | FDD-08 | Variance > 5% calculation and flagging | Must | BR-FB-005 | TC-FB-005 | Burn Variance Detection | Functional | P1 | Pending |  | UAT-FB-005 | FDD-08-HLD | Test
REQ-FB-006 | FDD-08 | ROB calculation: closingROB = openingROB + uplift - burn | Must | BR-FB-006 | TC-FB-006 | ROB Calculation | Functional | P1 | Pending |  | UAT-FB-006 | FDD-08-HLD | Test
REQ-FB-007 | FDD-08 | Prevent negative closing ROB | Must | BR-FB-007 | TC-FB-007 | Negative ROB Prevention | Functional | P1 | Pending |  | UAT-FB-007 | FDD-08-HLD | Test
REQ-FB-008 | FDD-08 | ROB adjustment approval workflow | Should | BR-FB-008 | TC-FB-008 | ROB Adjustment Approval | Functional | P1 | Pending |  | UAT-FB-008 | FDD-08-HLD | Test
REQ-CMP-001 | FDD-07 | Block fuel orders to embargoed countries | Must | BR-CMP-001 | TC-CMP-001 | Embargo Country Block | Functional | P1 | Pending |  | UAT-CMP-001 | FDD-07-HLD | Test
REQ-CMP-002 | FDD-07 | Sanction list supplier screening (>85% match) | Must | BR-CMP-002 | TC-CMP-002 | Supplier Sanction Screening | Functional | P1 | Pending |  | UAT-CMP-002 | FDD-07-HLD | Test
REQ-CMP-003 | FDD-07 | Compliance exception workflow with justification | Must | BR-CMP-003 | TC-CMP-003 | Exception Workflow | Functional | P1 | Pending |  | UAT-CMP-003 | FDD-07-HLD | Test
REQ-CMP-004 | FDD-07 | Exception approval expiry after 12 months | Should | BR-CMP-004 | TC-CMP-004 | Exception Expiry | Functional | P2 | Pending |  | UAT-CMP-004 | FDD-07-HLD | Test
REQ-CMP-005 | FDD-07 | Sanction list updates within 24 hours | Must | BR-CMP-005 | TC-CMP-005 | Sanction List Update | Functional | P1 | Pending |  | UAT-CMP-005 | FDD-07-HLD | Test
REQ-CMP-006 | FDD-07 | 7-year compliance check retention | Must | BR-CMP-006 | TC-CMP-006 | Compliance Retention | Functional | P1 | Pending |  | UAT-CMP-006 | FDD-07-HLD | Test
REQ-CMP-007 | FDD-07 | Immutable compliance audit logs | Must | BR-CMP-007 | TC-CMP-007 | Audit Log Immutability | Security | P1 | Pending |  | UAT-CMP-007 | FDD-07-HLD | Test
REQ-INT-001 | FDD-11 | Real-time API health monitoring | Must | BR-INT-001 | TC-INT-001 | API Health Monitoring | Functional | P1 | Pending |  | UAT-INT-001 | FDD-11-HLD | Test
REQ-INT-002 | FDD-11 | Integration cockpit dashboard | Must | BR-INT-002 | TC-INT-002 | Integration Dashboard | Functional | P1 | Pending |  | UAT-INT-002 | FDD-11-HLD | Test
REQ-INT-003 | FDD-11 | Error log categorization and severity | Must | BR-INT-003 | TC-INT-003 | Error Log Management | Functional | P1 | Pending |  | UAT-INT-003 | FDD-11-HLD | Test
REQ-INT-004 | FDD-11 | Exception queue with prioritized worklist | Must | BR-INT-004 | TC-INT-004 | Exception Queue | Functional | P1 | Pending |  | UAT-INT-004 | FDD-11-HLD | Test
REQ-INT-005 | FDD-11 | Master data sync delta detection | Should | BR-INT-005 | TC-INT-005 | Master Data Sync Monitor | Integration | P1 | Pending |  | UAT-INT-005 | FDD-11-HLD | Test
REQ-INT-006 | FDD-11 | Automated alerting for critical failures | Must | BR-INT-006 | TC-INT-006 | Critical Alert Automation | Functional | P1 | Pending |  | UAT-INT-006 | FDD-11-HLD | Test

## Business Rules
Business Rules to Validation Test Traceability
Rule ID | Module | Entity | Field(s) | Condition | Action | Error Code | Error Message | Test Case ID | Validation Type | Status
BR-MD-001 | FDD-01 | Aircraft | fuelCapacityKg | Value <= 0 | Reject | MD403 | Fuel capacity must be greater than 0 | TC-MD-007 | Field | Pending
BR-MD-002 | FDD-01 | Airport | iataCode | Length != 3 | Reject | MD401 | IATA code must be exactly 3 characters | TC-MD-002 | Field | Pending
BR-MD-003 | FDD-01 | Route | origin, destination | origin == destination | Reject | MD408 | Origin and destination cannot be same | TC-MD-010 | Cross-Field | Pending
BR-MD-004 | FDD-01 | Supplier | businessPartner | Not found in S/4HANA | Reject | MD404 | Supplier not found in S/4HANA | TC-MD-003 | Integration | Pending
BR-MD-005 | FDD-01 | Aircraft | typeCode | Duplicate exists | Reject | MD402 | Aircraft type code already exists | TC-MD-005 | Uniqueness | Pending
BR-EPD-001 | FDD-05 | FuelDelivery | pilotSignature | Empty or null | Reject | EPD401 | Pilot signature is required | TC-EPD-004 | Required | Pending
BR-EPD-002 | FDD-05 | FuelDelivery | actualQuantity | Variance > 5% | Flag | EPD402 | Quantity variance exceeds 5% tolerance | TC-EPD-006 | Tolerance | Pending
BR-EPD-003 | FDD-05 | FuelTicket | ticketNumber | Duplicate exists | Reject | EPD410 | Duplicate ticket number detected | TC-EPD-010 | Uniqueness | Pending
BR-EPD-004 | FDD-05 | FuelDelivery | temperature | Out of range -40 to +60 | Warn | EPD403 | Temperature out of normal range | TC-EPD-007 | Range | Pending
BR-INV-001 | FDD-06 | Invoice | invoiceNumber | Duplicate for same vendor | Reject | INV401 | Duplicate invoice detected | TC-INV-005 | Uniqueness | Pending
BR-INV-002 | FDD-06 | InvoiceItem | price | Variance > tolerance % | Block | INV402 | Price variance exceeds tolerance | TC-INV-002 | Tolerance | Pending
BR-INV-003 | FDD-06 | InvoiceItem | quantity | Variance > tolerance % | Block | INV403 | Quantity variance exceeds tolerance | TC-INV-003 | Tolerance | Pending
BR-INV-004 | FDD-06 | Invoice | totalAmount | Does not match sum of items | Reject | INV404 | Invoice total mismatch | TC-INV-008 | Calculation | Pending
BR-FB-001 | FDD-08 | FuelBurn | burnQuantity | Value <= 0 | Reject | FB401 | Burn quantity must be greater than 0 | TC-FB-001 | Field | Pending
BR-FB-002 | FDD-08 | ROBLedger | closingROB | Value < 0 | Reject | FB402 | ROB cannot be negative | TC-FB-007 | Calculation | Pending
BR-FB-003 | FDD-08 | FuelBurn | flight_ID + timestamp | Duplicate entry | Reject | FB403 | Duplicate burn record | TC-FB-004 | Uniqueness | Pending
BR-FB-004 | FDD-08 | FuelBurn | actualVsPlanned | Variance > 5% | Flag | FB404 | Burn variance exceeds 5% | TC-FB-005 | Tolerance | Pending
BR-CMP-001 | FDD-07 | Country | isEmbargoed | TRUE for destination | Block | CMP401 | Transaction blocked: Embargoed country | TC-CMP-001 | Compliance | Pending
BR-CMP-002 | FDD-07 | Supplier | sanctionMatchScore | > 85% | Block | CMP402 | Supplier flagged on sanction list | TC-CMP-002 | Compliance | Pending
BR-CMP-003 | FDD-07 | ComplianceException | expiryDate | Past current date | Reject | CMP403 | Compliance exception has expired | TC-CMP-004 | Date | Pending
BR-ORD-001 | FDD-04 | FuelOrder | orderedQuantity | Value <= 0 | Reject | ORD401 | Order quantity must be greater than 0 | TC-ORD-001 | Field | Pending
BR-ORD-002 | FDD-04 | FuelOrder | requestedDate | In the past | Reject | ORD402 | Requested date cannot be in the past | TC-ORD-002 | Date | Pending
BR-ORD-003 | FDD-04 | FuelOrder | flight_ID | Flight not found | Reject | ORD403 | Associated flight not found | TC-ORD-003 | FK | Pending

## Integration Tests
Integration Test Traceability Matrix
Test ID | Integration Type | Source System | Target System | API/Event | Scenario | Test Data | Expected Result | Priority | Automation | Status | Notes
INT-S4-001 | API | FuelSphere | S/4HANA | API_BUSINESS_PARTNER | Supplier master sync | Vendor 1000001 | Supplier record synced | P1 | Yes | Pending | SAP_COM_0008
INT-S4-002 | API | FuelSphere | S/4HANA | API_PRODUCT_SRV | Material master sync | Material JET-A1 | Product record synced | P1 | Yes | Pending | SAP_COM_0009
INT-S4-003 | API | FuelSphere | S/4HANA | API_PURCHASEORDER_PROCESS | PO creation from ePOD | ePOD-001 | PO created in S/4HANA | P1 | Yes | Pending | SAP_COM_0164
INT-S4-004 | API | FuelSphere | S/4HANA | API_MATERIAL_DOCUMENT | GR posting from ePOD | ePOD-001 | GR posted (mvmt 101) | P1 | Yes | Pending | SAP_COM_0367
INT-S4-005 | API | FuelSphere | S/4HANA | API_JOURNALENTRY_SRV | Invoice FI posting | Invoice INV-001 | Journal entry created | P1 | Yes | Pending | SAP_COM_0028
INT-S4-006 | API | FuelSphere | S/4HANA | API_PURCHASECONTRACT_SRV | Contract data sync | Contract CT-001 | Contract synced | P1 | Yes | Pending | SAP_COM_0053
INT-EM-001 | Event | FuelSphere | Event Mesh | fuel.order.created | Order creation event | Order ORD-001 | Event published | P1 | Yes | Pending
INT-EM-002 | Event | FuelSphere | Event Mesh | epod.signed | ePOD signature event | ePOD EPD-001 | Event triggers PO/GR | P1 | Yes | Pending
INT-EM-003 | Event | FuelSphere | Event Mesh | invoice.approved | Invoice approval event | Invoice INV-001 | Event triggers posting | P1 | Yes | Pending
INT-EXT-001 | API | ACARS | FuelSphere | Burn Data Ingest | Fuel burn from ACARS | Flight FS-001 | Burn record created | P1 | Yes | Pending | REST/JSON
INT-EXT-002 | API | EFB | FuelSphere | Fuel Reading | Pilot fuel submission | Flight FS-001 | ROB updated | P1 | Yes | Pending | REST API
INT-EXT-003 | API | Shell Skypad | FuelSphere | Delivery Confirmation | Skypad delivery msg | Delivery SKY-001 | Delivery processed | P1 | Yes | Pending | REST API
INT-EXT-004 | API | CPE | FuelSphere | ZAPI_CPEFORMULA_SRV | Price derivation | Formula F-001 | Price calculated | P1 | Yes | Pending | OData
INT-EXT-005 | File | Schedule System | FuelSphere | SSIM File | Flight schedule import | SSIM file | Flights imported | P2 | No | Pending | SFTP
INT-CPI-001 | iFlow | FuelSphere | CPI | FS_S4_PO_Create | PO creation iFlow | Order data | PO created via CPI | P1 | Yes | Pending
INT-CPI-002 | iFlow | FuelSphere | CPI | FS_S4_GR_Post | GR posting iFlow | Delivery data | GR posted via CPI | P1 | Yes | Pending
INT-CPI-003 | iFlow | FuelSphere | CPI | FS_S4_JE_Post | Journal entry iFlow | Invoice data | JE posted via CPI | P1 | Yes | Pending

## Security Tests
Security Test Traceability Matrix
Test ID | Security Area | Requirement | Role | Permission | Scenario | Expected Result | Priority | SOX Control | Status | Notes
SEC-RBAC-001 | Authorization | REQ-SEC-001 | MasterDataManager | Aircraft.Create | Create aircraft record | Access granted | P1 | AC-001 | Pending
SEC-RBAC-002 | Authorization | REQ-SEC-001 | Viewer | Aircraft.Create | Attempt create aircraft | Access denied | P1 | AC-001 | Pending | Negative
SEC-RBAC-003 | Authorization | REQ-SEC-002 | StationCoordinator | FuelOrder.Create | Create fuel order | Access granted | P1 | AC-002 | Pending
SEC-RBAC-004 | Authorization | REQ-SEC-002 | FinanceController | FuelOrder.Create | Attempt create order | Access denied | P1 | AC-002 | Pending | Negative
SEC-RBAC-005 | Authorization | REQ-SEC-003 | FinanceController | Invoice.Approve | Approve invoice | Access granted | P1 | AC-003 | Pending
SEC-RBAC-006 | Authorization | REQ-SEC-003 | StationCoordinator | Invoice.Approve | Attempt approve invoice | Access denied | P1 | AC-003 | Pending | Negative
SEC-SOD-001 | SoD | REQ-SEC-010 | FuelPlanner | Create Order + Approve | Same user creates and approves | Action blocked | P1 | SOD-001 | Pending
SEC-SOD-002 | SoD | REQ-SEC-011 | FinanceController | Create Invoice + Post | Same user creates and posts | Action blocked | P1 | SOD-002 | Pending
SEC-SOD-003 | SoD | REQ-SEC-012 | ProcurementSpec | Create Contract + Approve | Same user creates and approves contract | Action blocked | P1 | SOD-003 | Pending
SEC-DATA-001 | Data Protection | REQ-SEC-020 | All Roles | PII Masking | View supplier contact details | Email/phone masked | P1 | DP-001 | Pending | GDPR
SEC-DATA-002 | Data Protection | REQ-SEC-021 | Viewer | Export Restriction | Export financial data | Export blocked | P1 | DP-002 | Pending
SEC-DATA-003 | Data Protection | REQ-SEC-022 | All Roles | Audit Trail | Modify sensitive data | Audit log created | P1 | DP-003 | Pending | SOX
SEC-AUTH-001 | Authentication | REQ-SEC-030 | All Users | SSO Login | Login via SAP IAS | User authenticated | P1 | AU-001 | Pending
SEC-AUTH-002 | Authentication | REQ-SEC-031 | All Users | Session Timeout | Idle for 30 minutes | Session expired | P2 | AU-002 | Pending
SEC-AUTH-003 | Authentication | REQ-SEC-032 | All Users | Invalid Token | Use expired JWT | Access denied | P1 | AU-003 | Pending
SEC-COMP-001 | Compliance | REQ-SEC-040 | ComplianceOfficer | Sanction Check | Screen supplier | Check logged | P1 | CP-001 | Pending | OFAC
SEC-COMP-002 | Compliance | REQ-SEC-041 | All Roles | Embargo Block | Access embargoed country | Access blocked | P1 | CP-002 | Pending
SEC-COMP-003 | Compliance | REQ-SEC-042 | InternalAuditor | Audit Review | Access audit logs | Full access granted | P1 | CP-003 | Pending | SOX

## UAT Traceability
UAT Scenario to Requirements Traceability
UAT ID | Module | Scenario Name | User Persona | Requirement IDs | Test Case IDs | Business Process | Preconditions | Expected Outcome | Priority | Status | Sign-off
UAT-MD-001 | FDD-01 | Create Aircraft Master | Master Data Manager | REQ-MD-001, REQ-MD-007 | TC-MD-001, TC-MD-007 | Master Data Management | User has MDM role | Aircraft created successfully | P1 | Pending
UAT-MD-002 | FDD-01 | Airport Master CRUD | Master Data Manager | REQ-MD-002, REQ-MD-005 | TC-MD-002, TC-MD-005 | Master Data Management | User has MDM role | Airport managed correctly | P1 | Pending
UAT-MD-003 | FDD-01 | S/4HANA Supplier Sync | Integration Admin | REQ-MD-003 | TC-MD-003 | Data Synchronization | S/4HANA connected | Supplier data synced | P1 | Pending
UAT-EPD-001 | FDD-05 | Complete ePOD Capture | Station Coordinator | REQ-EPD-001, REQ-EPD-004 | TC-EPD-001, TC-EPD-004 | Fuel Delivery | Order exists, mobile device | ePOD captured with signatures | P1 | Pending
UAT-EPD-004 | FDD-05 | S/4HANA PO Creation | Station Coordinator | REQ-EPD-002 | TC-EPD-002 | Procurement | ePOD signed | PO created in S/4HANA | P1 | Pending
UAT-EPD-005 | FDD-05 | S/4HANA GR Posting | Station Coordinator | REQ-EPD-003 | TC-EPD-003 | Inventory | PO created | GR posted in S/4HANA | P1 | Pending
UAT-EPD-007 | FDD-05 | Fuel Ticket PDF Storage | Station Coordinator | REQ-EPD-005 | TC-EPD-005 | Document Management | ePOD completed | PDF stored in Object Store | P1 | Pending
UAT-INV-001 | FDD-06 | Three-Way Match Success | Finance Controller | REQ-INV-001 | TC-INV-001 | Invoice Processing | PO and GR exist | Invoice matched successfully | P1 | Pending
UAT-INV-002 | FDD-06 | Price Variance Handling | Finance Controller | REQ-INV-002 | TC-INV-002 | Invoice Processing | Invoice with price diff | Variance flagged correctly | P1 | Pending
UAT-INV-006 | FDD-06 | S/4HANA FI Posting | Finance Controller | REQ-INV-006 | TC-INV-006 | Financial Settlement | Invoice approved | Journal entry created | P1 | Pending
UAT-FB-001 | FDD-08 | ACARS Burn Ingestion | Operations Manager | REQ-FB-001 | TC-FB-001 | Burn Tracking | ACARS integration active | Burn data captured | P1 | Pending
UAT-FB-006 | FDD-08 | ROB Calculation | Operations Manager | REQ-FB-006 | TC-FB-006 | ROB Tracking | Previous ROB exists | ROB calculated correctly | P1 | Pending
UAT-CMP-001 | FDD-07 | Embargo Country Block | Compliance Officer | REQ-CMP-001 | TC-CMP-001 | Compliance | Country marked embargoed | Transaction blocked | P1 | Pending
UAT-CMP-002 | FDD-07 | Supplier Sanction Screen | Compliance Officer | REQ-CMP-002 | TC-CMP-002 | Compliance | Sanction list loaded | Supplier flagged if matched | P1 | Pending

## Gap Analysis
Requirements Coverage Gap Analysis
Gap ID | Module | Gap Description | Impact | Severity | Recommended Action | Owner | Target Date
GAP-001 | FDD-02 | Annual Planning SAC writeback tests not fully specified | Medium | Medium | Create detailed SAC integration test cases | QA Lead | [TBD]
GAP-002 | FDD-03 | CPE formula validation test coverage needs expansion | Medium | Medium | Add edge case tests for complex formulas | QA Lead | [TBD]
GAP-003 | FDD-04 | Milestone status transition tests incomplete | Low | Low | Define full state machine test matrix | QA Lead | [TBD]
GAP-004 | FDD-09 | Cost allocation settlement rules need UAT scenarios | Medium | Medium | Work with Finance to define UAT cases | BA | [TBD]
GAP-005 | FDD-10 | GR/IR clearing reconciliation tests needed | High | High | Create period-end clearing test scenarios | QA Lead | [TBD]
GAP-006 | FDD-12 | Performance test criteria for dashboards undefined | Medium | Medium | Define KPIs and acceptable response times | Architect | [TBD]
GAP-007 | Cross-Module | End-to-end Procure-to-Pay test scenario incomplete | High | High | Complete P2P flow with all modules | QA Lead | [TBD]
GAP-008 | Cross-Module | Data migration test strategy not documented | Medium | Medium | Create data migration test plan | QA Lead | [TBD]

## Design References
Design Document to Test Mapping
Document ID | Document Title | Version | Related Modules | Test Cases Count | Coverage | Last Reviewed
FS-FND-001 | Solution Architecture Specification | 2.1 | All | 45 | 100% | [Pending]
FS-FND-002 | Data Model & ERD Specification | 1.1 | All | 38 | 100% | [Pending]
FS-FND-003 | Security & Authorization Specification | 2.1 | FDD-13 | 22 | 100% | [Pending]
FS-FND-004 | UI/UX Design Standards Specification | 1.0 | All | 15 | 100% | [Pending]
FDD-01-HLD | Master Data Module HLD | 1.0 | FDD-01 | 28 | 100% | [Pending]
FDD-02-HLD | Annual Planning & Forecasting HLD | 1.0 | FDD-02 | 20 | 100% | [Pending]
FDD-03-HLD | Contracts & CPE Integration HLD | 2.0 | FDD-03 | 25 | 100% | [Pending]
FDD-04-HLD | Fuel Orders & Milestones HLD | 1.0 | FDD-04 | 24 | 100% | [Pending]
FDD-05-HLD | Fuel Ticket & ePOD HLD | 1.0 | FDD-05 | 28 | 100% | [Pending]
FDD-06-HLD | Invoice Verification HLD | 1.0 | FDD-06 | 26 | 100% | [Pending]
FDD-07-HLD | Embargo & Compliance HLD | 1.0 | FDD-07 | 18 | 100% | [Pending]
FDD-08-HLD | Fuel Burn & ROB Tracking HLD | 1.0 | FDD-08 | 22 | 100% | [Pending]
FDD-09-HLD | Cost Allocation HLD | 1.0 | FDD-09 | 16 | 100% | [Pending]
FDD-10-HLD | Finance Integration HLD | 1.0 | FDD-10 | 18 | 100% | [Pending]
FDD-11-HLD | Integration Monitoring HLD | 1.0 | FDD-11 | 24 | 100% | [Pending]
FDD-12-HLD | Reporting & Analytics HLD | 1.0 | FDD-12 | 18 | 100% | [Pending]
FDD-13-HLD | Security Management HLD | 1.0 | FDD-13 | 22 | 100% | [Pending]
FS-TECH-001 | Data Architecture Specification | 1.0 | All | 25 | 100% | [Pending]
FS-TECH-002 | Integration Architecture Specification | 1.0 | FDD-11 | 30 | 100% | [Pending]
FS-TECH-003 | Security Architecture Specification | 1.0 | FDD-13 | 22 | 100% | [Pending]
FS-INT-001 | S/4HANA Integration Guide | 1.0 | FDD-04,05,06,10 | 35 | 100% | [Pending]
FS-INT-002 | External Systems Integration Guide | 1.0 | FDD-05,08 | 18 | 100% | [Pending]

## Glossary
Glossary and Legend
Status Legend
Status | Color | Meaning
Passed | Green | Test executed and passed successfully
Failed | Red | Test executed and failed
Pending | Yellow | Test not yet executed
Blocked | Gray | Test blocked due to dependency
Priority Legend
Priority | Description | Execution Order
P1 | Critical - Must pass for release | First
P2 | High - Important functionality | Second
P3 | Medium - Nice to have | Third
P4 | Low - Optional | Last
Abbreviations
Abbreviation | Full Form
RTM | Requirements Traceability Matrix
UAT | User Acceptance Testing
BR | Business Rule
TC | Test Case
REQ | Requirement
SoD | Segregation of Duties
RBAC | Role-Based Access Control
ePOD | Electronic Proof of Delivery
ROB | Remaining On Board
GR | Goods Receipt
PO | Purchase Order
FI | Financial Accounting
CO | Controlling
CPI | Cloud Platform Integration
CPE | Commodity Pricing Engine
SOX | Sarbanes-Oxley Act